## Cycle Time and Process Efficien
CYCLE TIME & PROCESS EFFICIENCY ANALYSIS
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3568 | Top Track ASSY | 4 | 4, 3, 3 | 15, 16, 17 | 2 Hrs 42 Mins | 1 Hr 49 Mins | 4 Hrs 9 Mins | Crane wait time was over 25 mins, Skilled man power was not available, A Template would be helpful. | 22 Hrs 48 Mins | 13 Hrs 20 Mins
E – A3568 | Bottom Track ASSY | 5 | 4 | 15 + OT(3.30 Hrs) | 57 Mins | - | 1 Hr 7 Mins | Fetching tools was the only drawback. | 11 Hrs 5 Mins | 9 Hrs 1 Min
E – 3571 | Truss ASSY | 4 | 4 | 15 + OT(1.30 Hrs) | 58 Mins | - | 3 Hrs 11 Mins | Crane wait time was over the Limit, Team Went to do other Job & was helping others. | 7 Hrs 13 Mins | 4 Hrs 4 Mins
E – 3571 | Bottom Track ASSY | 5 | 5 | 16, 17 | 1 Hrs 44 Mins | - | 2 Hr 8 Mins | Fetching tools was the only drawback, Material out of stock. | 11 Hrs 25 Mins | 7 Hrs 8 Mins
E – A3568 | Incline Track ASSY | 3 | 3 | 16, 17 | 1 Hrs 44 Mins | - | 34 Mins | Waited for Top Track to be completed, Team Went to do other Job & was helping others, (1.49 Hrs) – Waited on 16th for Top Track. | 11 Hrs 52 Mins | 7 Hrs 53 Mins
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3568 | U – Clamp & Placing The Glass | 4 & 5 | 4 & 9 | 19 | 40 Mins | - | 13 Mins | Unnecessary man power was Consumed. 7 is Optimal. | 2 Hrs 49 Mins | 1 Hr 56 Mins
E – A3568 | Motor Mount Adjustment | 3 | 3 | 19 | 49 Mins | REWORK | 17 Mins | This can be avoided if the labour Is a little more conscious. | 5 Hrs 6 Mins | 4 Hrs
E – A3568 | Bottom Truss Electrical Wiring | 4 | 1 | 19 | 56 Mins | 19 Mins | 26 Mins | Unnecessary movement, Huge intervals, Highly inefficient. | 4 Hrs 51 Mins | 3 Hrs 10 Mins
E – A3568 | Top Truss Electrical Wiring | 4 | 1 | OT(3 Hrs) On 19 | - | - | - | - | 3 Hrs | 3 Hrs
E – A3573 | Truss ASSY | 5 | 5 | 20 | 48 Mins | - | 36 Mins | Crane wait time was over 36 mins. | 3 Hrs 56 Mins | 2 Hrs 32 Mins
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3571 | Top Track ASSY | 4 | 4, 5 | 19, 20 | 1 Hr 48 Mins | 1 Hr 9 Mins | 3 Hrs 17 Mins | Waiting for welder was over 51 Mins. | 17 Hrs 28 Mins | 11 Hrs 14 Mins
E – A3568 | Escalator Step Final Assembly | 4 | 8 – 9 | 19, 20, 21 | 2 Hrs 41 Mins | - | 5 Hrs 53 Mins | 7 is Optimal(Man Power), Material fetching time should be Reduced. | 20 Hrs 41 Mins | 12 Hrs 7 Mins
E – A3571 | Incline Track ASSY | 3 | 3 | 20 | 47 Mins | - | 13 Mins | - | 5 Hrs 53 Mins | 4 Hrs 53 Mins
E – A3573 | Heat - Induced Realignment | 2 | 2 | 20 | - | - | 18 Mins | Measuring technique is very old, Accuracy is about 80% – 90%, It is not Optimal. | 1 Hr 41 Mins | 1 Hr 23 Mins
E – A3571 | Step Installation | 4 | 7 | 21 | 9 Mins | 39 Mins | 14 Mins | 5 is Optimal(Man Power), Rework was done by 2 persons, Reason : Misalignment. | 3 Hrs 22 Mins | 2 Hrs 11 Mins
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3573 | Bottom Track ASSY | 5 | 5 | 20, 21 | 1 Hr 1 Min | - | 1 Hr 29 Mins | Fetching tools was the only drawback. | 10 Hrs 39 Mins | 8 Hrs 9 Mins
E – A3573 | Top Track ASSY | 4 | 4 | 21, 22 | 1 Hr 53 Mins | 40 Mins + OT | 2 Hrs 8 Mins | Can be completed within 10 Hrs, Lacking skilled labour. | 16 Hrs 28 Mins | 11 Hrs 47 Mins
E – A3568 | Hand Rail Alignment, Top & Bottom Step Assy Alignment | 2 | 2 | 21 | 1 Hr 1 Min | 39 Mins | 43 Mins | Labour was gone to fix alignment problem. | 7 Hrs 35 Mins | 5 Hrs 12 Mins
E – A3573 | Incline Track Profiling | 3 | 2 | 21 | 52 Mins | - | 12 Mins | - | 4 Hrs 20 Mins | 3 Hrs 16 Mins
E – A3571 | Escalator Step Final Assembly | 7 | 9 | 21, 22, 23 | 2 Hrs 4 Mins | - | 3 Hrs 44 Mins | 7 is Optimal(Man Power), Material fetching time should be Reduced. | 19 Hrs 34 Mins | 13 Hrs 46 Mins
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3575 | Heat - Induced Realignment | 2 | 2 | 22 | - | - | 11 Mins | Measuring technique is very old, Accuracy is about 80% – 90%, It is not Optimal. | 1 Hr 39 Mins | 1 Hr 28 Mins
E – A3575 | Bottom Track ASSY | 5 | 4, 5 | 22, 23 | 1 Hr 5 Mins | - | 53 Mins | - | 9 Hrs 34 Mins | 7 Hrs 36 Mins
E – A3571 | Bottom Truss Electrical Wiring | 4 | 1 | 23 | 53 Mins | - | 1 Hr 33 Mins | Unnecessary movement, Huge intervals, Highly inefficient. | 6 Hrs 25 Mins | 3 Hrs 59 Mins
TIME TUNING
JOB NO | TASK | MAN POWER |  | DATE | NON – PRODUCTIVE TIME |  |  | REMARKS | TIME TAKEN | ACTUAL TIME
|  | PLAN | ACTUAL |  | BREAK | REWORK | FETCHING TOOLS
E – A3575 | Top Track ASSY | 5 | 5 | 29, 30 | 1 Hr 10 Mins | - | 13 Mins | Main drive alignment was a issue for 15 Mins. | 10 Hrs 29 Mins | 9 Hrs 6 Mins
E – A3572 | Top Track ASSY | 5 | 4, 1, 4 | 31, 2 + 1 – OT (8 Hrs) | 57 Mins | - | 15 Mins | - | 10 Hrs 35 Mins | 9 Hrs 23 Mins
E – A3572 | Escalator Step Final Assembly | 7 | 9 | 4, 5 | 1 Hr 43 Mins | - | 7 Mins | 7 is Optimal(Man Power). | 14 Hrs 36 Mins | 12 Hrs 14 Mins
E – 8835 | Escalator Step Final Assembly | 7 | 9 | 9, 10 | 1 Hr 13 Min | - | 16 Mins | 7 is Optimal(Man Power). | 13 Hrs 12 Mins | 11 Hrs 43 Mins

## NVA - Break Down
NON – VALUE ADDED BREAK DOWN
JOB NO | TASK | NON – VALUE ADDED
|  | MAN |  | MACHINE |  |  | MATERIAL |  | METHOD
|  | BREAK | LUNCH | CRANE | WELDING &FLAMETHROWER | DRILL & GRINDER | STORE | WORKER | TOOLS | SKILL | FREE ROAM / NO WORK | REWORK
E – A3568 | Truss ASSY | 11 Mins | 36 Mins | 39 Mins | - | - | - | - | - | - | 19 Mins | -
| Heat - Induced Realignment | - | - | - | 11 Mins | - | - | - | 9 Mins | - | 14 Mins | -
| Top Track ASSY | 49 Mins | 1 Hr 51 Mins | 36 Mins | 13 Mins | 9 Mins | 57 Mins | 42 Mins | 53 Mins | 1 Hr 9 Mins | 37 Mins | 50 Mins
| Bottom Track ASSY | 18 Mins | 39 Mins | - | 15 Mins | 11 Mins | - | 17 Mins | 16 Mins | - | 15 Mins | -
| Incline Track ASSY | 32 Mins | 1 Hr 12 Mins | - | 34 Mins | - | - | - | - | - | 1 Hr 41 Mins | -
| Step Installation | 19 Mins | - | 16 Mins | - | - | - | 23 Mins | 15 Mins | 11 Mins | 13 Mins | -
| Step Alignment | 15 Mins | 38 Mins | - | - | 23 Mins | - | - | - | - | - | 1 Hr 7 Mins
| Escalator Final Assembly | 1 Hr 24 Mins | 1 Hr 59 Mins | 22 Mins | 27 Mins | 38 Mins | 1 Hr 37 Mins | 46 Mins | 1 Hr 28 Mins | 16 Mins | 41 Mins | -
SUB TOTAL |  | 3 Hrs 48 Mins | 6 Hrs 55 Mins | 1 Hrs 53 Mins | 1 Hrs 40 Mins | 1 Hrs 12 Mins | 2 Hrs 34 Mins | 2 Hrs 8 Mins | 2 Hrs 52 Mins | 1 Hrs 36 Mins | 4 Hrs 0 Mins | 1 Hrs 57 Mins
TOTAL |  | 7 Hrs 36 Mins |  | 5 Hrs 39 Mins |  |  | 5 Hrs 8 Mins |  | 11 Hrs 28 Mins
JOB NO | TASK | NON – VALUE ADDED
|  | MAN |  | MACHINE |  |  | MATERIAL |  | METHOD
|  | BREAK | LUNCH | CRANE | WELDING & FLAMETHROWER | DRILL & GRINDER | STORE | WORKER | TOOLS | SKILL | FREE ROAM / NO WORK | REWORK
E – A3571 | Truss ASSY | 16 Mins | 42 Mins | 1 Hr 48 Mins | - | - | - | - | - | - | 23 Mins | -
| Heat - Induced Realignment | - | - | - | 23 Mins | - | - | - | 8 Mins | - | 11 Mins | -
| Top Track ASSY | 37 Mins | 1 Hr 11 Mins | - | 51 Mins | - | 34 Mins | 24 Mins | 1 Hr 32 Mins | 34 Mins | 31 Mins | -
| Bottom Track ASSY | 39 Mins | 1 Hr 5 Min | 33 Mins | - | - | 28 Mins | 11 Mins | 41 Mins | - | 18 Mins | -
| Incline Track ASSY | 8 Mins | 39 Mins | - | 13 Mins | - | - | - | 5 Mins | - | 11 Mins | -
| Step Installation | 9 Mins | 35 Mins | 17 Mins | - | - | - | 27 Mins | - | - | 1 Hr 49 Mins | -
| Step Alignment | 7 Mins | 32 Mins | - | - | 9 Mins | - | - | 14 Mins | - | 12 Mins | -
| Escalator Final Assembly | 36 Mins | 1 Hr 28 Mins | 15 Mins | - | 11 Mins | 1 Hr 8 Mins | 21 Mins | 1 Hr 33 Mins | - | 16 Mins | -
SUB TOTAL |  | 2 Hrs 8 Mins | 6 Hrs 12 Mins | 2 Hrs 53 Mins | 1 Hrs 27 Mins | 0 Hrs 11 Mins | 2 Hrs 10 Mins | 1 Hrs 23 Mins | 4 Hrs 0 Mins | 0 Hrs 34 Mins | 3 Hrs 51 Mins | 0 Hrs 0 Mins
TOTAL |  | 4 Hrs 16 Mins |  | 8 Hrs 39 Mins |  |  | 4 Hrs 20 Mins |  | 16 Hrs 0 Mins
JOB NO | TASK | NON – VALUE ADDED
|  | MAN |  | MACHINE |  |  | MATERIAL |  | METHOD
|  | BREAK | LUNCH | CRANE | WELDING & FLAMETHROWER | DRILL & GRINDER | STORE | WORKER | TOOLS | SKILL | FREE ROAM / NO WORK | REWORK
E – A3573 | Truss ASSY
Heat - Induced Realignment
Top Track ASSY
| Bottom Track ASSY | [10 empty] | -
| Incline Track ASSY | [10 empty] | -
| Step Installation | [10 empty] | -
Step Alignment
Escalator Final Assembly
SUB TOTAL |  | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
TOTAL |  | 0 Hrs 0 Mins |  | 0 Hrs 0 Mins |  |  | 0 Hrs 0 Mins |  | 0 Hrs 0 Mins

## Final Report
CYCLE TIME & PROCESS EFFICIENCY ANALYSIS
JOB NO | TASK | MAN POWER |  | CYCLE PLAN TIME | NON – VALUE ADDED |  |  |  | ACTUAL CYCLE TIME | TOTAL CYCLE TIME | REMARKS
|  | PLAN | ACTUAL |  | MAN | MACHINE | MATERIAL | METHOD
E – A3568 | Truss ASSY | 4 | 5 | 5 Hrs | 47 Mins | 39 Mins | - | 19 Mins | 4 Hrs 41 Mins | 0 Hrs 0 Mins | Crane wait time was over 39 mins.
| Heat - Induced Realignment | 2 | 2 | 3 Hrs | - | 11 Mins | - | 23 Mins | 1 Hr 53 Mins | 0 Hrs 0 Mins | Measuring technique is very old, Accuracy is about 80% – 90%, It is not Optimal.
| Top Track ASSY | 5 | 4 | 10 Hrs | 2 Hrs 42 Mins | 58 Mins | 1 Hr 39 Mins | 3 Hr 29 Mins | 13 Hrs 20 Mins | 0 Hrs 0 Mins | Crane wait time was over 35 mins, Skilled man power was not available, There was a rework for almost 2 Hrs, A Template would be helpful.
| Bottom Track ASSY | 5 | 4 | 8 Hrs | 57 Mins | 19 Mins | 17 Mins | 31 Mins | 9 Hrs 1 Min | 0 Hrs 0 Mins | Fetching tools was the only drawback.
| Incline Track ASSY | 4 | 3 | 8 Hrs | 1 Hr 44 Mins | 34 Mins | - | 1 Hr 41 Mins | 7 Hrs 53 Mins | 0 Hrs 0 Mins | Waited for Top Track to be completed, Team Went to do other Job & was helping others, (1.41 Hrs) – Waited on 16th for Top Track.
| Step Installation | 5 | 7 | 7 Hrs | 19 Mins | 14 Mins | 23 Mins | 39 Mins | 4 Hrs 47 Mins | 0 Hrs 0 Mins | 5 is Optimal(Man Power), Skilled man power was not available.
| Step Alignment | 2 | 2 | 6 Hrs | 53 Mins | 23 Mins | - | 1 Hr 7 Mins | 5 Hrs 12 Mins | 0 Hrs 0 Mins | Personnel were sent to correct the alignment fault, Adding one more skilled person would improve efficiency.
| Escalator Final Assembly | 7 | 9 | 13 Hrs | 3 Hrs 21 Mins | 1 Hr 27 Mins | 2 Hrs 23 Mins | 2 Hrs 16 Mins | 14 Hrs 3 Mins | 0 Hrs 0 Mins | 7 is Optimal(Man Power), Material was not on time, Welding machine was not on time.
SUB TOTAL |  | 34 | 36 | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
| Total Man Hour | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
JOB NO | TASK | MAN POWER |  | CYCLE PLAN TIME | NON – VALUE ADDED |  |  |  | ACTUAL CYCLE TIME | TOTAL CYCLE TIME | REMARKS
|  | PLAN | ACTUAL |  | MAN | MACHINE | MATERIAL | METHOD
E – A3571 | Truss ASSY | 4 | 5 | 5 Hrs | 58 Mins | 1 Hr 48 Mins | - | 23 Mins | 4 Hrs 49 Mins | 0 Hrs 0 Mins | Crane wait time was over the Limit, Team Went to do other Job & was helping others.
| Heat - Induced Realignment | 2 | 2 | 3 Hrs | - | 23 Mins | - | 19 Mins | 1 Hr 23 Mins | 0 Hrs 0 Mins | Measuring technique is very old, Accuracy is about 80% – 90%, It is not Optimal.
| Top Track ASSY | 5 | 5 | 10 Hrs | 1 Hr 48 Mins | 51 Mins | 58 Mins | 2 Hr 37 Mins | 11 Hrs 14 Mins | 0 Hrs 0 Mins | Waiting for welder was over 51 Mins.
| Bottom Track ASSY | 5 | 5 | 8 Hrs | 1 Hrs 44 Mins | 33 Mins | 39 Mins | 59 Mins | 9 Hrs 8 Mins | 0 Hrs 0 Mins | Fetching tools was the only drawback, Material out of stock.
| Incline Track ASSY | 4 | 3 | 8 Hrs | 47 Mins | 13 Mins | - | 16 Mins | 7 Hrs 35 Mins | 0 Hrs 0 Mins | Track profiling takes almost 40% of the time.
| Step Installation | 5 | 7 | 7 Hrs | 44 Mins | 17 Mins | 27 Mins | 1 Hr 49 Mins | 5 Hrs 49 Mins | 0 Hrs 0 Mins | 5 is Optimal(Man Power), Rework was done by 2 persons, Reason : Misalignment.
| Step Alignment | 2 | 2 | 6 Hrs | 39 Mins | 9 Mins | - | 26 Mins | 5 Hrs 37 Mins | 0 Hrs 0 Mins | Adding one more skilled person would improve efficiency.
| Escalator Final Assembly | 7 | 9 | 13 Hrs | 2 Hrs 4 Mins | 26 Mins | 1 Hr 29 Mins | 1 Hrs 49 Mins | 13 Hrs 46 Mins | 0 Hrs 0 Mins | 7 is Optimal(Man Power), Material fetching time should be Reduced.
SUB TOTAL |  | 34 | 38 | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
| Total Man Hour | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
JOB NO | TASK | MAN POWER |  | CYCLE PLAN TIME | NON – VALUE ADDED |  |  |  | ACTUAL CYCLE TIME | TOTAL CYCLE TIME | REMARKS
|  | PLAN | ACTUAL |  | MAN | MACHINE | MATERIAL | METHOD
E – A3573 | Truss ASSY | 4 | 5 | 5 Hrs | 48 Mins | 44 Mins | - | 51 Mins | 4 Hrs 32 Mins | 0 Hrs 0 Mins | Crane wait time was over 40 Mins, Unskilled handling.
| Heat - Induced Realignment | 2 | 2 | 3 Hrs | - | 17 Mins | - | 27 Mins | 1 Hr 41 Mins | 0 Hrs 0 Mins | Measuring technique is very old, Accuracy is about 80% – 90%, It is not Optimal.
| Top Track ASSY | 5 | 4 | 10 Hrs | 1 Hr 53 Mins | 22 Mins | 19 Mins | 2 Hrs 8 Mins | 11 Hrs 47 Mins | 0 Hrs 0 Mins | Can be completed within 10 Hrs, Lacking skilled labour.
| Bottom Track ASSY | 5 | 5 | 8 Hrs | 1 Hr 1 Min | 25 Mins | - | 1 Hr 7 Mins | 9 Hrs 9 Mins | 0 Hrs 0 Mins | Fetching tools was the only drawback.
| Incline Track ASSY | 4 | 3 | 8 Hrs | 49 Mins | 27 Mins | - | 13 Mins | 7 Hrs 45 Mins | 0 Hrs 0 Mins | Track profiling takes almost 40% of the time.
| Step Installation | 5 | 6 | 7 Hrs | 51 Mins | 15 Mins | - | 9 Mins | 5 Hrs 12 Mins | 0 Hrs 0 Mins | 5 is Optimal(Man Power), Skilled man power was not available.
| Step Alignment | 2 | 2 | 6 Hrs | 37 Mins | 21 Mins | - | 19 Mins | 5 Hrs 51 Mins | 0 Hrs 0 Mins | Adding one more skilled person would improve efficiency.
| Escalator Final Assembly | 7 | 9 | 13 Hrs | 1 Hr 9 Mins | 29 Mins | 2 Hr 56 Mins | 2 Hrs 7 Mins | 15 Hrs 27 Mins | 0 Hrs 0 Mins | 7 is Optimal(Man Power), Material fetching time should be Reduced.
SUB TOTAL |  | 34 | 36 | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins
| Total Man Hour | 0 Hrs 0 Mins | 0 Hrs 0 Mins | 0 Hrs 0 Mins

## Sheet2
capture the standard time with basic condition
compare with the standard and actual time
arrive the gap summary
consolidate the 4(M) – man machine material method
arrive the actions – sop,tools,facility
after implementing the action repeat the same
nvs breakup | manand method
add truss assyand heating
truss assy – 5 ppl, 6Hrs